## Slide 1: Project 573322-EPP-1-2016-IL-EPPKA2-CBHE-JP Curriculum Reform for Promoting Democratic Principles and Civic Education in Israel and In Georgia Field monitoring November 21, 2018 at Sapir Academic College, Sderot, Israel
Website: https://cure.erasmus-plus.org.il/

## Slide 2: What are our objectives?
What are the main objectives of your project: (Improve the level of competences and skills in HEIs by developing new and innovative education programmes and Foster regional integration and cooperation across different regions of the world through joint initiatives, sharing of good practices and cooperation.)
THROUGH:
Construct and Develop a Multi-Dimensional Program that promotes curricular reform for Democratic principles and civic education in Higher Educational Teacher-Training Institutions or Faculties/Departments in Israel and in Georgia
Develop innovative courses through international teams, pilot these course and integrate them into our curriculum of our HEIs.
“TRAIN THE TRAINERS” Workshops in EU institutions
Run faculty workshops
Establishing Centers for Civic Action on our Campuses
  Student Leadership Workshops and workshops aimed to provide them with tools to design and implement civic oriented projects.
  Student Activities that reflect civic involvement
  Course Promoting Active Citizenship
In-service teacher training workshops on civic education and guidance to set up civic clubs in the schools where the teacher’s teach.
Publish new learning materials and provide “kits” for our courses and student activities.
Under which priority(s) does your project fall: Curriculum Reform Joint Project
  Horizontal Priorities: promoting the professional development of staff and youth workers in ICT methodologies
  Facilitating the validation of non-formal and informal learning and its permeability with formal education pathways

## Slide 3: Highlight Facts& Figures
5 Courses have been developed (in application estimated around 40 pilots—in FACT we will have around 90 PILOTS!).
Georgian Readers/KITs for 3 courses have or are almost been completed. Kits are completed for 2 universal courses which are being taught frontally.
Centers of Social and Civic Involvement have been established in 9 universities and college.
  Within these centers STUDENT ACTIVITIES are being implemented. Each HEI is obligated to run at least 6 different activities over the 2 years of the pilot.
SMS TOT faculty training (to date 5 mobilities with the participation of 74 faculty members (not only CURE members)
Faculty trained in SMS are running workshops in their HEIs sharing knowledge and pedagogical tools (we estimate at least 50 different training sessions in total with the participation of at least 150-200 faculty members being trained).
In-service teacher training (we estimate at least 18 workshops with approximately 200 teachers benefitting from the program).
We have had 4 consortium meetings (Tbilisi, Haifa, Canterbury and Batumi). 5th consortium meeting is being planned for June 2018.
Followed through on Midterm recommendation of hiring an external evaluator to assess CURE courses and qualitative feedback from these courses.

## Slide 4: CURE’s Partners: Israeli, Georgian and EU HEIs.

## Slide 5
Academic Colleges of Education,
Departments/Faculty of Education in Universities,
Major Universities
Student Unions
NGO which are involved in civic action and leadership development.
Our Consortium

## Slide 6
15 Academic Institutions:
  5 in Israel—4 teaching colleges, 1 regional college.
  5 HEI Georgia including major cities and outlying areas.
  5 HEIs in the EU countries.
2 NGOs: (Georgia and Estonia)
9 Student Unions: 4 in Israel and 5 in Georgia
Working with 27 Groups:
17 Official Members of CURE with 9 student groups/unions

## Slide 7: Israeli CURE Team:
Gordon Academic College of Education (Coordinating Institution)
Sakhnin Academic College
David Yellin Academic College
Academic College of Education Givat Washington
Sapir Academic College

## Slide 8: GEORGIAN CURE TEAM:
Ilia State University (Tbilisi)
Ivane Javakhishvili Tbilisi State University
Samtskhe-Javakheti State University (Alhaltzeche).
Shota Rustaveli State University (Batumi)
Kutaisi University
Civic Development Institute (NGO, Tbilisi)

## Slide 9: EUROPEAN UNION CURE TEAM
University of Education Upper Austria
Paris-Lodron-University of Salzburg, Austria
Canterbury Christ Church University, United Kingdom
Tallin University, Estonia
Jagiellonian University, Poland
Jaan Tõnissoni Instituut, Estonia

## Slide 10: Why is our project important?
Tell us what is the need for the project: Students need to be prepared to be active citizens (EHEA ND Bolonga process “Good citizens are not born but are made”).
TEACHERS have Pivotal Role in preparing next generation of citizens but there is no official curricula committed to developing active citizenship in teacher-training programs in Israel and in Georgia (only technical training on political state structures).
NEED FOR ISRAEL: deepening socio-economic, cultural and religious gaps create an unequal and fragmented society (OECD 2014 IL report). Need for civic awareness and involvement.
NEED FOR GEORGIA: Georgia is a post-communist society-low level of civic awareness reported in Human Rights Watch 2014. None of the state HEIs that train teachers have a program for active citizenship or civic education. Desperately need a curriculum.

## Slide 11: How do your activities address this need: CURE’s curriculum reform will enhance the quality of CE in CURE's teacher-training programs both for our faculty as well as for our students, who are future educators of our societies. The faculty, teachers and students who benefit from CURE’s program will be able to effectively present, discuss and challenge the rudimentary notions of civic involvement in our society. Moreover as educators, they will help shape knowledge, perceptions and attitudes towards responsible citizenship within a democratic setting, encourage critical thought and enactment of civil rights, actions and duties within their own classrooms thus sustaining and multiplying the program aims. This program does this THROUGH:
1. Developing and implementing a comprehensive program of courses and student activities that promotes civic education and behavior within our TT program.
2. Integrating these courses into the curriculum in partner HEI.
3. Faculty and Teacher Workshops
4. Courses and activities will integrate innovative pedagogy that will strengthen the aims and objectives of the courses (e.g. PBL, Service-Based Learning, VaKE; experiential and peer learning and teaching; integrating new technology in teaching and learning, etc.).
5. Create course kits that will enable other professionals and teachers to benefit from the CURE’s innovative courses.
6. Establish an international network of professionals who collaborate together, share knowledge and good practices.
7. Establish centers for promoting CE on campus and in schools.
8. Create a website to disseminate program.
9. Publish results and strategies (online and hard copy): articles and handbooks.

## Slide 12: Explain how your project relates to your institutional / faculty strategic plan
GACE: Promoting pluralistic and Democractic values is part of our MISSION STATEMENT at GACE and relates directly to the courses we are developing and our student activities
Social and Civic involvement in the community of all members of Gordon College is part of our strategic mission. Mandatory volunteering of students, institutionalizing the Center for Civic and Social Involvement, inclusion of faculty and staff in volunteering (October 2018 mission statement of the President).
Continuous Improvement of the quality of Learning, Teaching and Research of our faculty is related to our SMS program.

## Slide 13: HOW PROJECT RELATES TO INSTIUTIONAL/DEPARTMENT/FACULTY STRATEGIC PLAN of Givat Washington Academic College
Social and Civic Involvement is an integral part of the Academic Studies as well as part of Teachers training.
Programs and activities include on campus and off campus community programs emphasizing Jewish Values, Democracy and Education for Civic Involvement.
Implementation of Academic syllabus pertaining to Sustainability , Community involvement and Democracy in Education, Physical Education, Science, Literature, ESL, and Early Childhood courses.

## Slide 14
3.3.1 Continuous updating of teaching methods will be based on the experience of participating into international projects;
Benefit from CURE:
VAKE methodology
Community/Service/Problem based Learning
Technology and Pedagogy (Tallinn Trainings)
KUTAISI UNIVERSITY

## Slide 15
Existing academic programs (curriculum, syllabus) will be revised: The content of the program and / or its components (courses) will be replaced if necessary, the volume, the calendar plan of training, the methods of assessing the learning and learning outcomes will be amended if necessary;
We have integrated 3 CURE pilot Courses into our 2 existing courses.
CEDG KU 1
CES KU 1
PAC KU 1
1. Democracy and Citizenship
It was piloted in spring 2018
1. Democracy and Citizenship
It will be piloted in spring 2019
2. Ecology and Natural Resource Economics
It is being piloted now
KUTAISI UNIVERSITY

## Slide 16
5.3.4 Appropriate financial support for projects and activities initiated by student self-government in terms of civil and social activities
KUTAISI UNIVERSITY

## Slide 17
Strategic Objective:
Infrastructure Development
Task 1.1 Improvement of the study-research environment
Task 1.2 Development of the material-technical base of the library
Task 1.3 Creating a comfortable environment for independent work and relaxation of students
- Open public space will be constructed in the back yard of the university building;
- Students’ inner free public space will be perfected;
- "CreaLab" and the “Center for Social and Civic Involvement” will be equipped with 3D printer and other innovative devices;
Benefit from CURE: Krakow trainings on Public Sphere and Public spaces.
The room for the Center for Civic and Social Involvement
KUTAISI UNIVERSITY

## Slide 18: David Yellin Academic College Mission and Strategic Goals
The College fosters social involvement and social-educational entrepreneurship in cooperation with civil society organizations in Jerusalem and in Israel. The students among civil society organizations in terms of cumulative hours annually. Social involvement is intended only for Lake activities and develop.
the College is committed to the following core values, which espouses: education for tolerance and against violence to existing education excellence multicultural education in Israel society the involvement of development of education combining people with diverse needs
מעורבות חברתית
הובלה בפיתוח מקצועי של עובדי הוראה
שילוב אנשים עם צרכים מגוונים בחברה
באמצעות יישום ערכים אלה אנו יכולים להוביל מהלכים לעיצוב פני החברה בישראל בשנים הבאות.

## Slide 19: Ilia State U
The mission of Ilia State University is the creation, transmission and use of knowledge for advancement of science and public development at both local and international levels. The education school relies on the University's Mission, responding to the modern challenges of education and contributes to the development of education science and educational system.
All this can not be achieved without the establishment of civil values in students.
Thus, the University School of Education is one of the main strategic directions of the value of competences in training courses focused on the development of a new paradigm of teaching introduction to prospective values were civilian trains and their own competence and scope of competence of these frames is distributed.
Based on the strategic goals of the Ilia State University and the School of Education, it has already begun to integrate the materials within the project in the Teacher Training Program at Faculty of Sciences and Arts: Methods of Teaching in Social Sciences at the Primary Level, Interdisciplinary approaches to teaching History, The basics of teaching History, Ethics of school relations, Values Education, Civic Education for Sustainability and The Promoting Active Citizenship through VaKE method.

## Slide 20: What has been achieved so far ?
Working Package 1 : Preparation: For details for each partner please refer to midterm report’s table of achieved results.

## Slide 21: Working Package 1 : Preparation: For details for each partner please refer to midterm report’s table of achieved results.
Comments | Actual Outcomes | What actually happened | Activities according to original work plan | Team | WP | 
 | All institutions partners learned about CURE and recruitment of key people brought into the program | CURE was presented to key stakeholders (administrative, department heads, faculty and student leaders/union) | Meetings | ALL institutions | 1.1 | Meeting key stakeholders of IL and GEO
 | framework plans. key events and deliverables presented to participants. Each institution presented their aims and roles in the project. Working teams for developing courses and student activities formed. Introduction preparatory work for First Consortium Meeting Information about the project financing. | Two meetings occurred, one in Israel and one in Georgia with around 15-20 people participating in each meeting. | IL/GEO National meetings | Georgian and Israeli HEIs | 1.2 | Meetings in IL and GEO
 | Getting to know different institutions (presentations) EU presentation of their approaches to promoting Democracy and Civic Education Working Teams formed for Courses, QA, and Steering committee, portal, centers for social involvement, Special Mobility Strand, dissemination. By the end of the meetings drafts of work plans were completed International Student leadership workshops: 4 topics (Social sustainability, Core values for change, Local story, Active project) were discussed during the Student Leadership workshop and the topics of future student activities had been defined. | Kick off meeting occurred with participation of around 90 faculty, administrative staff and student | Kickoff meeting Received authorization for key stakeholders to also participate | Whole consortium | 1.3 | Kickoff Consortium meeting
 | Presentation of EU teams of their approaches to promoting active citizenship at their HEIs, Drafts of SMS work plan set up with deadline set for the July 2017 meeting, Decision to change SMS so each partner HEI would benefit from the training offered at 5 EU HEIs. | Each EU partner presented their methods for promoting civic involvement and education. | Workshops and presentations. Modified SMS program | Faculty of all CURE HEIs | 1.4 | Good Practices in Learning EU Approaches to CE
 | Workplans of the different working teams were completed for Courses, QA, and Steering committee, portal, centers for social involvement, Special Mobility Strand, dissemination. Link to summary of workplans in WP1 : https://cure.erasmus-plus.org.il/course/view.php?id=63 | Working Teams formed | KOM | Whole consortium | 1.5 | Establishment of Working teams
 | Working draft of QA document https://cure.erasmus-plus.org.il/course/view.php?id=63 in WP3 ubnit. | Completed working draft | Working draft of QA | CCCU, JU, TSU, GACE | 1.6 | Preparing QA

## Slide 22: WP2.1 : DEV P1. Constructing a dynamic program and strategies that promote curricular reform for civic education .
Comments | Actual Outcomes | What actually happened | Activities according to original work plan | Team | WP | 
 | https://cure.erasmus-plus.org.il/course/view.php?id=66 | Agendas of meeting completed and work teams ready for CM | Work teams begin dev tasks | IL/GE HEIs | 2.1 | Internal meetings
 | https://cure.erasmus-plus.org.il/ click on courses to access all courses | All syllabi completed | Syllabi completed | All | 2.2 | Dev of Syllabi
 | Access website to see what has been accomplished https://cure.erasmus-plus.org.il/course/view.php?id=62 | 5 SMS programs completed | SMS Workshop Dev | ALL | 2.3 | Dev Facult WS
 | https://cure.erasmus-plus.org.il/ click on student activities | Programs developed | Work plans completed | IL/GEO | 2.4 | Developing Students Activities Workshops.
 | https://cure.erasmus-plus.org.il/course/view.php?id=69 | Course developed | IL + GEO course dev | IL/GEO | 2.5 | Dev of inservice teacher WS
 | https://cure.erasmus-plus.org.il/course/view.php?id=63 WP 4 unit has Diss plan | Plan developed and ratified in CM2 | Draft Completed | GACE/SJSU/JTI/SAP | 2.6 | DEV of Diss, plan
 | https://cure.erasmus-plus.org.il/course/view.php?id=8 | Development of all programs | Working team | ALL | 2.7 | Consortium Meeting 2
 | https://cure.erasmus-plus.org.il/course/view.php?id=9 |  | Development and fine tuning | ALL | 2.8 | Consortium meeting 3

## Slide 23: WP2.2 : Development Part 2: Implementation of Developed Pilot Programs :
Comments | Actual Outcomes | What actually happened | Activities according to original work plan | Team | WP | 
 | Outcomes related to course objectives Application estimated 40 courses—doubling that | Over 80 courses listed for the next 2 years with 2,500+ students | Courses listed | IL/GE/TU/PHOO/PLUS | 2.21-2 | Listing CURE’s courses and pilots
 |  |  | National and internal meetings | IL/GE | 2.23 | Faculty Meetings (within HEI and between National HEI)
 | https://cure.erasmus-plus.org.il/ click on student activities | At least 3 events a year for each Georgian and Israeli HEI |  | IL/GE | 2.24 | Student activities
 | Teachers are receiving tools to have small activities in their classroom (being followed through in 3rd year). | Professional training workshops | Enrichment courses for teachers running | IL/GE | 2.25 | Teacher-training workshops and establishing centers in schools
 | YEAR 3 of project |  | Year 3 | IL/GE | 2.26 | Student National Meetings
 | QA and EV processes set in motion for last year including EU monitoring . KITs and Readers moved forward. Dissemination events finalized. https://cure.erasmus-plus.org.il/course/view.php?id=10 | Fine tuning, student workshops, QA and DISS, work on course kits |  | ALL | 2.27 | Consortium Meeting # 4
 | From Beginning of project CURE’s website please click on student activites | Ongoing | CM1,2,4 + in HEIs | IL/GE | 2.28 | Student Leadership Workshop

## Slide 24: WP2.3Development (Part 3): Developing CURE’s On-Line Platforms :
Comments | Actual Outcomes | What actually happened | Activities according to original work plan | Team | WP | 
 | https://cure.erasmus-plus.org.il/ | DESIGNED | ACCOMPLISHED | SAP + consortim | 2.31 | Designing CURE’s Online Platform
 | https://cure.erasmus-plus.org.il/ | DEVELOPED AND MAINTAINED | ACCOMPLISHED | SAP | 2.32 | Development and Maintenance of Consortium Site within CURE’s Online Moodle platform.
 | https://cure.erasmus-plus.org.il/ | ACCOMPLISHED | ACCOMPLISHED | SAP | 2.33 | Development of public CURE’s online platform site for distant learning course, dissemination and exploitation
Not fully developed and the coordinator needs to encourage more CURE team members to upload pages. | Faculty have uploaded and developed personal pages. | Continually developed | In progress | ALL | 2.34 | Educators’ Personal Areas

## Slide 25: WP 3: Quality Plan
Comments | Actual Outcomes | What actually happened | Activities according to original work plan | Team | WP | 
Totally accomplished | All assessment tools were developed and uploaded to the portal to be used. https://cure.erasmus-plus.org.il/course/view.php?id=63 WP#3 unit. | Tools were developed Quality Framework plan completed and approved by consortium. | accomplished | EU team + TSU + GACE | 3.1 | Development of Assessment tools
In Additon to the CURE EU QA team we have an external auditor of the courses program as recommended by our officer. | Protocol for summarizing questionnaires established. Portal organized for uploading of summary. | In progress | In progress | EU team | 3.2 | Assessing Pilot Programs and Writing Reports
We need to upload the schedules and guidelines to the portal. | Schedules and guiidelines are complete | Guidelines for the field monitoring developed and approved. Schedules established for field monitoring | In Year 3 of the program | EU team | 3.3 | Field Monitoring visits of EU members to IL and GEO

## Slide 26: WP 4: Dissemination and Exploitation
Comments | Actual Outcomes | What actually happened | Activities according to original work plan | Team | WP | 
All HEIs are fully committed to program and ALL Key stakeholders at HEIs know about CURE | All HEIs have publicized CURE through their website and internal workshops Examples of LINKS on Webpages at CURE HEIs : https://www.int.gordon.ac.il/capacity-building-ka2 https://www.sapir.ac.il/en/content/4274 http://www.dyellin.ac.il/about/overseasrelations/international-collaborations/cure https://ph-ooe.at/studium/international/projects/democracy-and-civic-education.html http://www.unik.edu.ge/ | Fully Accomplished | Internal meetings with Key stakeholders and dissemination within the institution | ALL | 4.1 | Dissemination within HEIs
 | 0ngoing https://cure.erasmus-plus.org.il/ We have had over 30,000 page views from over 53 countries (August 1, 2018 details) | Virtual : managed in IL | All going according to planned | SAP managing with ALL consortium contact people participatings | 4.2 | CURE’s Online: MOODLE Workstation, Website
 | CURE's facebook: https://www.facebook.com/We-are-CURE-282491268849278/ https://www.facebook.com/groups/1864512057094561/ CURE’s facebook page for Georgian team : https://www.facebook.com/groups/795414607265523/ Example of a CURE's YouTube video clip: https://www.youtube.com/watch?v=wQRZsfQ2tDU&index=12&list=PLLOd54ID2dZOkW_cfRCVBpiw0YfEkTVL7 | Ongoing an accomplished. | All going according to planned | ALL members | 4.3 | Online Social-Professional Networking Platforms

## Slide 27: WP 4: Dissemination and Exploitation continued
Comments | Actual Outcomes | What actually happened | Activities according to original work plan | Team | WP | 
We will be asking for an extension of one full semester so that we can totally achieve the objectives of SMS programs and assess the impact of this program. | 75 faculty members have been trained over the year at our 5 EU HEIs. Internal faculty training have been running mentoring sessions or workshops sharing knowledge and tools of EU training. FOR DETAILS please go to SMS page: https://cure.erasmus-plus.org.il/course/view.php?id=62 | Competed first year of training at each EU HEI. | DELAYED ONE YEAR DUE TO THE FACT THAT FORMS WERE NOT READY | ALL members | 4.4 | Faculty Training workshops and Mentoring Includes SMS program
 | In-Service teachers have been receiving tools: https://bsu.edu.ge/sub-41/page/6109/index.html Education for democratic citizenship ad Human Rights. https://bsu.edu.ge/sub-41/page/6110/index.html Education in Multicultural environment https://bsu.edu.ge/sub-41/page/6108/index.html Democracy and Human Rights | Each HEI in IL and GEO has been implementing this program | Teacher-training has begun in Year 2 of program | IL/GEO HEIs | 4.5 | Profession Continued Education Courses for teachers
CURE’s major international conference will be within http://conf2019.macam.ac.il/ Authorization of PO Roisn McCabe to participate fully in this 3 day conference, adding these days to our planned 5th consortium meeting. | CURE is being known throughout IL and GEO as well as in EU countries. Using Ministry of Ed. + Mofet’s June 2019 conference for major dissemination event | Participating in numerous national and international conferences | ongoing | All consortium | 4.6 | Participating in National and International Conferences
Georgians have expanded the kits into readers accompanying 3 courses. | Please refer to course section of our portal | KITs-Readers to accompany 3 courses complete in Georgian Kits in English available for 2 universal courses. | Ongoing and accomplished | ALL members | 4.7 | Publications including Publishing Handbooks

## Slide 28: WP 5: Management
Comments | Actual Outcomes | What actually happened | Activities according to original work plan | Team | WP | 
 | First Kick-off meeting established Steering Committee and the committee met. They reviewed the application and the role of the steering committee. They felt that the roles as defined as adequate and that they would meet periodically or when an issue arose that required their intervention. | https://cure.erasmus-plus.org.il/mod/folder/view.php?id=2220 summary of meeting and decisions made. | YES | Everyone | 5.1 | Control and Monitoring: Setting up a Steering Committee
 | Communication has been reinforced through periodic SKYPE, national, international and specific meetings with all partners, phone conference calls, CURE’s website announcements and working areas. | Summary of meetings with outcomes: https://cure.erasmus-plus.org.il/course/view.php?id=63 | YES | Everyone | 5.2 | Quality Communication
 | Coordinator maintains constant communication with all members of the consortium and is assisted by ISU + TSU and EU members (for QA of academic program, CSCI and student activities). Periodic Field monitoring visits to GE and IL HEIs supports management process. July 2017 FM trip to GE : 4 HEIs were visited and meetings with Key Stakeholders, CURE’s faculty and students. all HEIs emphasized their commitment to the project objectives, goals and programs. Each HEI has a contact member who is responsible for project implementation and reporting to Coordinator. | Different aspects of program are implementing according to work plan, Number of key stakeholders met, agenda and summaries of meetings, expressed commitment of partners to implement program. Example of outcomes of July field monitoring : https://cure.erasmus-plus.org.il/mod/folder/view.php?id=2244 | YES | Everyone | 5.3 | Management of Program
 | GACE (assisted by ISU in GE) overseeing financial management : periodic reporting and uploading of documents in portal, workshops and individual mentoring sessions at national and international meetings. | Number of reports and documents uploaded to portal and financial reports of each HEI + Summary excel financial annex form. https://cure.erasmus-plus.org.il/course/index.php?categoryid=13 | YES | Everyone | 5.4 | Financial Management

## Slide 29: How did we prepare?
Describe the preparation stage of your project: Skype and national meetings to prepare for the first kickoff meeting which began the process of sharing good practices, setting up working teams and in sharing knowledge and establishing collaborative ties.
What were the outcomes/outputs from this stage? And what have you learned? Completely accomplished LFM aims. Refer to https://cure.erasmus-plus.org.il/course/view.php?id=7
Any changes to your work plan as a result? Key Stakeholders participated in this meeting and there was a change was in mobility plan—switching consortium meeting #2 from David Yellin to Gordon College and Consortium meeting #3 from Linz to Canterbury. ALL CHANGES AUTHORIZED.
Anything wasn’t achieved as planned? Why? Everything was accomplished.
How did this stage assist with your impact assessment? It was very important as in order to have an impact—we need to have partners “buying into the project”. This was fully achieved through the participation of key stakeholders and in the formation of integrated working teams and good team leaders.
FROM LFM:
Outputs (tangible) and Outcomes (intangible):
WP1: Outputs (OP): CURE FW to present good practices and set up working teams (WT). Outcomes (OC): Knowledge shared and Collaborative relations established
Indicators of progress:
Periodic reports that present WT work plans to WP leader; Exchange that is documented in group emails and use of the moodle work station.
How indicators will be Measured:
The quality of the content in the written reports; the use of the moodle work station for collaborative work, feedback from members about the quality of collaboration. Information uploaded to Web-portal
Notes: Was a baseline established in order to assess the change following the project?

## Slide 30: How and what was developed?
Describe the main outcomes of the development: All outcomes of WP2 completely accomplished (courses, programs and centers established). Refer to website for details: https://cure.erasmus-plus.org.il/
Are students involved in the development stage? In what way? Student leaders are involved in developing activities for the Centers of Civic and Social Involvement.
What is the role of the EU partners? EU partners have been actively involved in course development and academic QA. They are responsible for WP3 (Quality Plan and Evaluation) of our project.
Describe the involvement of your Associate Partners. (Not relevant).
What are the remaining main activities of the project: Continued piloting of all programs, National and international conference events, printing and publishing of materials to disseminate at our conferences, CURE EU field monitoring in IL/GEO; continuous evaluation and assessment.
Outputs (tangible) and Outcomes (intangible):
WP2 and WP 2.2: Tangible Outputs: 5 Courses, Student Activities, Centers of Social and Civic Involvement, SMS program, Website, IN-service teacher-training program, faculty training programs were all developed and are now being implemented.
Website launched and a center of our work. Educational kits in English developed. Educational kits further expanded into Readers in Georgian.
OUTCOMES: Civic education, knowledge, values and behaviour is enhanced among target groups and the cultural of collaboration formed among all consortium members.

## Slide 31: Curriculum Development
List the courses and Modules developed for regular study program:
  Global challenges in the 21st Century to Promote Active Citizenship and Democracy.
    SUB TOPIC which requires code to enter due to copyright issues: Digital Citizenship in the Globally Connected World.
  Civic Education for Sustainability
  Promoting Active Citizenship
  Civic Education and Democracy in Israel: Challenges and Pathways
  Civic Education and Democracy in Georgia: Challenges and Pathways.
  Workshop developed for in-Service Teacher Professional training
Describe how and why the methodology was chosen : Bologna process applied. All syllabi have learning outcomes.
Elaborate on new introduced teaching methodologies and technologies : SMS program: Value and Knowledge Education; Community/Service/Problem/Project based learning; Development of Public Spheres; Innovative pedagogy of auto/biographical and narrative enquiry for active citizenship; Using Technology as a pedagogical approach in course design for active citizenship.
Are students involved in the development stage? YES-student leaders design activities for social and civic involvement.
What is the role of the EU partners? ALL EU partners belonged to one of the 3 universal course development teams. They reviewed the English versions of the Israeli and Georgian courses and provided feedback. They are involved in QA activities and evaluation.
Describe the involvement of your Associate Partners.NONE
Elaborate on the academic accreditation process and the sustainability plan for the courses. All courses are accredited. Refer to the link https://cure.erasmus-plus.org.il/course/view.php?id=63&notifyeditingon=1
Which academic level are your courses for: ALL LEVELS can use our courses due to the structure and design of our development.
Please refer to https://cure.erasmus-plus.org.il/course/view.php?id=63&notifyeditingon=1 Unit: WP2 excel document called Summary of CURE pilots for details.
Notes: How was the methodology decided

## Slide 32: Training
List the Training courses, describe their development process, their purpose and what you have learned from them https://cure.erasmus-plus.org.il/course/view.php?id=62 Presents ALL academic faculty training programs and the learning outcomes of each EU HEI.
Elaborate on new introduced content, methodologies and technologies:
  Complete mapping of this will be done by final report by our external evaluator who will: 1. analyze the 84 pilots of CURE and the material
What is the role of the EU partners? SMS training program is at their HEIs.
How did you evaluate the quality of these activities? Questionnaires are online and are filled out after each SMS activity
What are the outputs / change from these activities? Faculty integrate new methods of teaching and learning in to their courses.
Target Audience: Academic faculty: 74 different training mobilities
No. of Students trained: around 20 student leaders who participated in our leadership training workshops in 3 consortium meetings.
We estimate that from our above participants in our TOT program around 1000 academic faculty and teachers will be trained.
Notes: How was the methodology decided

## Slide 33
Ms. Nino Chikovani, Teacher Ivane Javakhishvili Tbilisi State University Participant of SMS in PHOO, Linz, Austria
23.12.2017
I would like to start a letter with expressing my gratitude to the project coordinators and organizers for giving me an opportunity to be the part of all the events that were taking place during our stay in Austria. I have much to say, but will try to be brief. The sessions and workshops conducted for us were crucially significant for our professional growth. There were accents made on contemporary teaching methodology such as community based learning which covered the topics like civic education, project based learning, multicultural and multilingual education, inclusive education, etc. Though I always try to follow up the pace of the challenges and demands to the modern teacher, the information shared with us was perceived and realized from a different angle that I hadn’t experienced so far, consequently it made me rethink of the approaches used by me in the classroom focusing more on my students’ future study outcomes. One of the most significant sessions was about inclusive education and a vivid emphasis on how much the country does to raise civic awareness of the importance of this issue starting everything with perfectly elaborated curricula, where a major accent is made on helping the children with special educational needs to adapt to the normal lifestyle and the society around them.

## Slide 34: Our Quality assurance mechanisms
How was the QA team chosen? Who does it include? EU team plus a member from ISU and GACE who have experience in QA process.
Is there an external evaluator? Yes (for course impact and quality analysis)
Are you using other ways to externally evaluate the quality of your results? Our CURE EU internal team is monitoring our project with field visits.
What is being assessed? ALL programs
Please also describe the methods of assessment. Which indicators are used? How were they chosen? Please read document called Quality Plan for CURE: Fine-Tuned and Final located in https://cure.erasmus-plus.org.il/course/view.php?id=63
How does the team communicate the findings? All findings for SMS results are open and can be accessed via the portal. In the final evaluation of the courses and other programs, project results will be available to consortium members and most likely open to the public (to be decided upon by the CURE EU QA team).

## Slide 35: Dissemination & exploitation
How was the Dissemination team chosen? IL/GEO/EU members who are experienced in dissemination were chosen to coordinate this WP. ALL consortium members active in dissemination. Coordinators: SSJU, GACE, JTI
How was the strategy for the work plan decided? Based on good practices and lessons learned from DOIT project.
Elaborate on exploitation mechanisms within your institution? Internal faculty training and opening up SMS to all faculty members. In all major faculty meetings (opening and closing of our academic semester) our HEIs present their KA2 programs.
To other HEIs in Israel? Through Professional Networking, national and international conferences : including with the Mofet Institute in Israel and the Teacher-Professional Training Institute in Georgia. Using other KA2 programs and partners to promote CURE (ASSET and SSU conference).
CURE’S OPEN WEBSITE: almost 34,000 hits to our website from 75 different countries. 1,141 users averaging over 4 sessions in our portal and viewing around 7 different pages!
To other relevant non-academic stakeholders? Centers for Social and Civic Involvement link up with other non-academic/social organizations (to be reported on in final report).
Attach
Dissemination plan Located in WP4: https://cure.erasmus-plus.org.il/course/view.php?id=63
Are your project outputs:
On the Erasmus+ Project Results Platform? Not yet only towards end of project
On your institution’s website? yes
on the Erasmus+ Israel website? yes

## Slide 36: CURE- Website statistics: November 1st ,2018
How many pages every viewer sees
Viewers from 75 Different Countries

## Slide 37
Different Countries that had Viewers Visit and USE CURE’s Website!

## Slide 38
Different Countries that had Viewers Visit and USE CURE’s Website (page 2)!

## Slide 39: The impact of our project:
Describe the actual change within your institution, contributed solely to the project (Different levels: students, other faculty members, in your department, in the management of the institution….)
  1. Centers for Social and Civic Involvement have been created and institutionalized (with staff) and students are designing and implementing programs in the community through these centers.
  New courses that never existed in our HEIs are now part of the curriculum or existing courses have been upgraded through integrating CURE’s units within them.
  Through SMS program Faculty were trained in new pedagogical methods and are applying them to their teaching
What has been/will be the national impact?
  In Georgia there will be a curriculum for civic education in HEI’s teacher-training programs which can be modelled in other institutions. The fact that our CURE HEIs are located in different regions of GEO will provide opportunities to exploit our program and impact different regions.
  In Israel, there will be new courses available for any HEI to tap into in order to update their programs for civic education.
  The Centers for Social and Civic Involvement in our IL and GEO HEIs provides a model that can be replicated in other HEIs and contributes to the community through their activities. The fact that CURE’s IL HEIs represent differed educational systems (Secular, Religious and Arab) provides opportunities for impacting wide range of populations..
  Each of our HEIs are connection with tens if not hundreds of schools where their students apprentice teach. These schools will be impacted through our students AND through our in-service teacher-training programs.
How is the impact (/change) is/will be measured?
  Creation of new courses, units and the feedback from the participants and beneficiaries of these course and units.
  Narrative Testimonies by participants
What are the new capacities (to be) built in your institution?
  Faculty professional development and training workshops improves the quality of teaching at our institutions
  New or modernized curriculum improves training for civic education and involvement
  Centers for social and civic involvement which generate activities for the community

## Slide 40: What we want to sustain:
Describe your strategy to sustain the project’s outputs within your specific HEI
  Courses will be sustained due to the flexible way in which they were developed that enables integrating CURE’s course units into existing courses
  Centers of Social and Civic Involvement are institutionalized and key stakeholders have made the commitment to sustain these Centers
  Continuing Professional workshops for teachers are part of our HEI’s agenda so these courses will be integrated within this program.
  Faculty who have been trained have Life-Long-Learning skills and knowledge which they are applying to all of their teaching.
Have you set down with your institutional / departmental management or any other relevant factor within your institution who is crucial for the implementation and sustainability of your outputs?
  The involvement of key stakeholders and faculty members in this project promotes the sustainability of all of our outputs (courses, activities, workshops, faculty training, etc.).

## Slide 41: How are we managing it all?
Describe how decisions are made and problems are solved.
  The application sets the guidelines for our program. Minor adjustments are made according to consensus and discussion. Applying Diversity management approach is used in both decision making and problem solving processes.
Describe the methods and frequency of communication – between the teams and with the coordinator.
  Communication is open and transparent and the coordinator is available for receiving any communication from a CURE member.
  Most email communications are answered with several hours and very rarely never more than one day.
  SKYPE meetings are held monthly with Coordinator of the Georgian team.
Is all information available and transparent to all partners?
  All information is in the portal and available and transparent to all partners.
How was the Partnership Agreement agreed upon?
  The coordinator used the TEMPLATE from Brussels as a model making minor adjustments and additions based on the experience of coordinating the DOIT project. Each institution received a draft of the partnership agreement for feedback. Each Bilateral agreement went through this process.
What’s the process of reporting to the coordinator?
  Periodic project reports and the uploading of information to the portal.
What are the management tools in place
  Diversity Management Tools and WEBSITE is the main work area for uploading documents and reports.

## Slide 42: Our financial management:
Were there any problems with the transfer of funds? Are all financial matters transparent between the partners? YES
Who keeps the supporting documents? Scanned copies are uploaded to portal for project coordinator and advisor to review.
How is finance reported to the coordinator? Periodic reports (every 6 months).
Were any changes made to the original equipment list to be purchased? YES. Why? Needs changed. What kind of change? Each HEI that wanted changes filled out a template designed by the coordinator and this request was sent to the PO who approved ALL requests.
Was equipment purchased? YES If so, was it registered in your HEIs inventory? YES Was an E+ sticker placed? YES
How do you ensure that all guidelines are respected? Our financial manager or advisor constantly reviews uploaded documents and reports. Our financial advisor to KA2 is very competent and updated on Guidelines. What are the working mechanisms with your Auditor? Auditor will be working with the hard copies at GACE….he will do a pre-audit examining all finances through midterm report to see if there are any irregularities that need to be addressed.
Please indicate:
% of budget use so far
Type of equipment purchased so far:
Computers & software
Audio-visual
Lab materials
Books/materials
Other

## Slide 43: How does the project address the Bologna Process?
Please describe how your project addresses and incorporates
Learning Outcomes?
ECTS?
Student centered learning?
ALL THIS IS ACCOMPLISHED IN OUR COURSES.
Read all about it:
http://ec.europa.eu/education/policy/higher-education/bologna-process_en

## Slide 44: Horizontal issues?
Refers to the extent to which the project is aligned with the EU policy objectives:
transparency and convergence tools developed in the context of the Bologna Process policies: ECTS, DS, study cycles, EQF, QA, etc.)
gender equality, social inclusion, youth unemployment, sustainable development, etc.)
All this is accomplished completely in Georgia. In Israel use of certain aspects of Bologna process (learning outcomes and QA)

## Slide 45: What we want to share with you:
This is for our efforts to represent Israeli participation in E+ and disseminate your important outcomes.
Please indicate special/unique stories that can be shared as an added value of the project?
Anything interesting you would like us to upload to our website for dissemination purposes?
Relevant Links:
Videos?
Facts & Figures
Other Outcomes?